## Sheet1
Production Implementation Step
API EXTERNAL: API Gateway dan Cassandra
1 | Penyesuaian perbedaan konfigurasi API Gateway dan Cassandra antara staging dan Production dilakukan H-2
1.a | Penyesuaian objek, policy dan lain lain | 11/13/2025 | 14:00 | 16:00 | 120 menit | Lukman SPS
1.b | Sync folder data Cassandra dari Production ke staging | 11/13/2025 | 21:00 | 21:30 | 30 menit | Lukman SPS
2 | Pada Server Staging, pastikan service API Gateway 7.7 May 25 dan Cassandra 4.1.8 pada server staging stopped: | 11/14/2025 | 18:00 | 18:05 | 5 menit | Lukman SPS
10.194.120.211 : API Gateway dan Cassandra
10.194.120.220 : API Gateway dan Cassandra
10.194.120.218 : Cassandra
3 | Rsync folder Axway-7.7.0 Staging ke Production, di mana dari Production akan tarik folder dari Staging server | 11/14/2025 | 22:00 | 23:00 | 60 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
rsync -avlHX apim@<IP_staging>:/apps/Axway-7.7.0-May25 /apps/
10.194.120.211 → 10.194.139.115
10.194.120.220 → 10.194.139.114
10.194.120.218 → 10.194.139.117
4 | Pada Production, Stop service service API Gateway v7.7-Aug23 dan Cassandra 4.0.10 | 11/15/2025 | 0:00 | 0:07 | 7 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Downtime
4.a | Disable port traffic melalui API Gateway Manager dashboard
4.b | Shutdown service nodemanager dan instance
4.c | Shutdown service Cassandra
/apps/Axway-7.7.0/cassandra/bin/nodetool drain
ps -ef¦grep cassandra
kill -9 <pid>
5 | Rename folder instalasi API Gateway 7.7-Aug23 dan Cassandra existing dari /apps/Axway-7.7.0 menjadi /apps/Axway-7.7.0_aug23 | 11/15/2025 | 0:07 | 0:09 | 2 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
6 | Masuk ke folder /apps/ lalu rename folder Axway-7.7.0_may25 menjadi Axway-7.7.0 | 11/15/2025 | 0:09 | 0:10 | 1 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
7 | Penyesuaian data Cassandra | 11/15/2025 | 0:10 | 0:25 | 15 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
7.a | Backup folder (by rename folder) data Cassandra 4.1.8 pada 10.194.139.114
7.b | Copy folder data Cassandra v4.0.10 ke Cassandra v4.1.8 pada 10.194.139.114
7.c | Start Cassandra ver 4.1.8 pada 10.194.139.114
/apps/Axway-7.7.0/cassandra/bin/cassandra
7.d | Upgrade SSTables ver 4.1.8 pada 10.194.139.114
cd /apps/Axway-7.7.0/cassandra/bin
./nodetool upgradesstables
7.e | Lakukan secara sekuensial step 7.a - 7.e pada Cassandra 4.1.8 di server 10.194.139.115 dan 10.194.139.117
7.f | Nodetool repair secara sekuensial pada seluruh node
7.g | Nodetool status dan login ke cassandra
8 | Start API Gateway v7.7-May25 pada server 10.194.139.115 | 11/15/2025 | 0:25 | 0:30 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
9 | Start API Gateway v7.7-May25 pada server 10.194.139.114 | 11/15/2025 | 0:30 | 0:35 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
10 | Install python 3 | 11/15/2025 | 0:35 | 0:40 | 5 menit | Danamon
API External: API Gateway Analytics
1 | Pastikan service Analytics stop pada server staging | 11/14/2025 | 18:05 | 18:07 | 2 menit | Lukman (SPS)
2 | Rsync folder Axway-7.7.0 dari Staging ke Prod | 11/14/2025 | 21:15 | 21:45 | 30 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
rsync -av1HX /apps/Axway-7.7.0 apim@ipremotehost:/apps/Axway-7.7.0_may25
10.194.120.232 → 10.194.56.165
3 | Matikan service API Gateway Analytics v7.7-Aug23 pada server Analytics Prod | 11/15/2025 | 1:00 | 1:02 | 2 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Downtime
Input command semua task dan spesifik detail nama folder
4 | Rename instalasi folder API Gateway Analytics v7.7-Aug23 /apps/Axway-7.7.0 menjadi /apps/Axway-7.7.0_aug23 | 11/15/2025 | 1:02 | 1:04 | 2 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
5 | Rename instalasi folder API Gateway Analytics v7.7-May25 ke existing name instalasi folder /apps/Axway-7.7.0 | 11/15/2025 | 1:04 | 1:05 | 1 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
6 | Start Service API Gateway Analytics v7.7-May25 10.194.56.165 | 11/15/2025 | 1:05 | 1:07 | 2 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Service Online
API External: Sandbox API Management
1 | Pada Server Staging, pastikan service API Gateway 7.7 May 25 dan Cassandra 4.1.8 pada server staging stopped: | 11/14/2025 | 18:10 | 18:15 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
10.194.120.216: API Gateway dan Cassandra
2 | Penyesuaian data cassandra
3 | Rsync folder Axway-7.7.0_may25_staging dari Staging ke Sandbox | 11/14/2025 | 21:25 | 22:25 | 60 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
rsync -av1HX /apps/Axway-7.7.0 apim@ipremotehost:/apps/Axway-7.7.0_may25
10.194.120.216 → 10.194.139.118
3 | Pada Sandbox, Stop service API Gateway v7.7-Aug23 dan Cassandra 4.0.10 | 11/15/2025 | 1:15 | 1:20 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Downtime
3.a | Disable port traffic
3.b | Shutdown service nodemanager dan instance
3.c | Stop service Cassandra
/apps/Axway-7.7.0/cassandra/bin/nodetool drain
ps -ef¦grep cassandra
kill -9 <pid>
4 | Rename folder instalasi API Gateway 7.7-Aug23 dan Cassandra existing dari /apps/Axway-7.7.0 menjadi /apps/Axway-7.7.0_aug23 | 11/15/2025 | 1:20 | 1:22 | 2 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
5 | Masuk ke folder /apps/ lalu rename folder Axway-7.7.0_may25 menjadi Axway-7.7.0 | 11/15/2025 | 1:22 | 1:23 | 1 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
7 | Start API Gateway v7.7-May25 pada server 10.194.139.118 | 11/15/2025 | 1:23 | 1:29 | 6 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Service Online
8 | Install python 3 pada Cassandra Server | 11/15/2025 | 1:29 | 1:34 | 5 menit | Danamon
API External: Sandbox API Portal
1 | Matikan service mysql dan httpd API Portal v7.7-May25 pada server Staging 10.194.120.215 | 11/14/2025 | 18:20 | 18:25 | 5 menit | Lukman (SPS)
systemctl stop mysqld
systemctl stop httpd
2 | Backup mysql dan htdoc di Server Staging 10.194.120.215 | 11/14/2025 | 18:25 | 19:00 | 35 menit | Lukman (SPS)
Confirm apakah ada lib yg diinstall di OS
2.a | Backup data mysql
cd /apps
tar czvf mysql_staging.tar.gz mysql/
cp mysql_staging.tar.gz /opt/backup_staging
2.b | Backup apiportal
cd /opt/axway/apiportal
tar cvzf htdoc_staging.tar.gz htdoc/
cp htdoc_staging.tar.gz /opt/backup_staging
2.c | Backup server.key, server.crt, apiportal-ssl.conf
cd /etc/httpd/conf.d/
cp server.crt server.key apiportal-ssl.conf /opt/backup_staging
2.d | Backup my.cnf
cp /etc/my.cnf /opt/backup_staging
2.e | backup certs_ssl
cp -r /etc/mysql/certs/ /opt/backup_staging
3 | rsync folder /opt/backup_staging to production 10.194.139.116 | 11/14/2025 | 21:35 | 22:25 | 50 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
4 | Stop service mysql dan httpd di Prod | 11/15/2025 | 1:40 | 1:45 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Downtime
systemctl stop mysqld
systemctl stop httpd
5 | Backup and rename existing folder mysql dan htdoc di prod | 11/15/2025 | 1:45 | 2:05 | 10 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
cd /apps
5.a | tar cvzf mysql_prod.tar.gz mysql/
mv mysql mysql_prod
5.b | cd /opt/axway/apiportal
tar cvzf htdoc_staging.tar.gz htdoc/
mv htdoc htdoc_prod
5.c | backup server.key, server.crt, apiportal-ssl.conf
cd /etc/httpd/conf.d/
5.d | mv server.crt server.key apiportal-ssl.conf /etc/backup_prod
5.e | backup my.cnf
mv my.cnf /etc/backup_prod
5.f | backup certs_ssl
mv /etc/mysql/certs/ certs_prod
6 | Kopikan file rsync dari staging ke path berikut di prod 10.194.139.116 | 11/15/2025 | 2:05 | 2:15 | 15 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
cd /opt/backup_staging
tar xvzf mysql_staging.tar.gz -C /apps
cd /opt/backup_staging
tar xvzf htdoc_staging.tar.gz -C /opt/axway/apiportal
cp -r /opt/backup_staging/certs /etc/mysql/
cd /opt/backup_staging
cp server.crt server.key apiportal-ssl.conf /etc/httpd/conf.d/
cp my.cnf /etc
7 | Start mysql | 11/15/2025 | 2:15 | 2:20 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
systemctl start mysqld
8 | Start apache web server | 11/15/2025 | 2:20 | 2:25 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Service Online
systemctl start httpd
API INTERNAL: API Gateway dan Cassandra
1 | Penyesuaian perbedaan konfigurasi API Gateway dan Cassandra antara staging dan Production dilakukan H-2
1.a | Penyesuaian objek, policy dan lain lain | 11/13/2025 | 14:00 | 16:00 | 120 menit | Naufal (SPS)
1.b | Sync folder data Cassandra dari Production ke staging | 11/13/2025 | 21:30 | 22:00 | 30 menit | Naufal (SPS)
2 | Pada Server Staging, pastikan service API Gateway 7.7 May 25 dan Cassandra 4.1.8 pada server staging stopped: | 11/14/2025 | 18:30 | 18:40 | 10 menit | Naufal (SPS)
DC1 (staging):
10.194.120.209 API Gateway
10.194.120.210 API Gateway
10.194.120.212 Cassandra
10.194.120.213 Cassandra
10.194.120.214 Cassandra
DC2 (staging)
10.192.120.208 API Gateway
10.192.120.207 API Gateway
10.192.120.204 Cassandra
10.192.120.205 Cassandra
10.192.120.206 Cassandra
3 | Rsync folder Axway-7.7.0 dari Staging ke Production | 11/14/2025 | 22:00 | 23:10 | 70 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
rsync -av1HX /apps/Axway-7.7.0 apim@ipremotehost:/apps/Axway-7.7.0_may25
DC1:
10.194.120.209 → 10.194.118.18
10.194.120.210 → 10.194.118.19
10.194.120.212 → 10.194.16.38
10.194.120.213 → 10.194.16.39
10.194.120.214 → 10.194.16.40
DC2:
10.192.120.208 → 10.192.118.18
10.192.120.207 → 10.192.118.19
10.192.120.204 → 10.192.40.38
10.192.120.205 → 10.192.40.39
10.192.120.206 → 10.192.40.40
4 | Pada Production, Stop service service API Gateway v7.7-Aug23 dan Cassandra | 11/15/2025 | 1:05 | 1:12 | 7 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup | Downtime
4.a | Disable port traffic melalui API Gateway Manager dashboard
4.b | Shutdown service nodemanager dan instance
4.c | Shutdown service Cassandra
/apps/Axway-7.7.0/cassandra/bin/nodetool drain
ps -ef¦grep cassandra
kill -9 <pid>
5 | Rename folder instalasi API Gateway 7.7-Aug23 dan Cassandra existing dari /apps/Axway-7.7.0 menjadi /apps/Axway-7.7.0_aug23 | 11/15/2025 | 1:12 | 1:14 | 2 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
6 | Masuk ke folder /apps/ lalu rename folder Axway-7.7.0_may25 menjadi Axway-7.7.0 | 11/15/2025 | 1:14 | 1:16 | 2 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
7 | Penyesuaian data Cassandra | 11/15/2025 | 1:16 | 1:31 | 15 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
7.a | Backup folder (by rename folder) data Cassandra 4.1.8 pada 10.194.120.212
7.b | Copy folder data Cassandra v4.0.10 ke Cassandra v4.1.8 pada 10.194.120.212
7.c | Start Cassandra ver 4.1.8 pada 10.194.120.212
/apps/Axway-7.7.0/cassandra/bin/cassandra
7.d | Upgrade SSTables ver 4.1.8 pada 10.194.120.212
cd /apps/Axway-7.7.0/cassandra/bin
./nodetool upgradesstables
7.e | Lakukan secara sekuensial step 9.a - 9.e pada Cassandra 4.1.8 di server lainnya: 10.194.120.213, 10.194.120.214, 10.192.120.204, 10.192.120.205 dan 10.192.120.206
7.f | Nodetool repair secara sekuensial pada seluruh node dimulai dari 10.194.120.212
7.g | Nodetool status dan login ke cassandra
8 | Start API Gateway v7.7-May25 pada server 10.194.139.115 | 11/15/2025 | 1:31 | 1:33 | 2 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup | Service Online
9 | Start API Gateway v7.7-May25 pada server 10.194.139.114 | 11/15/2025 | 1:33 | 1:35 | 2 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
10 | Install python 3 | 11/15/2025 | 1:35 | 1:40 | 5 menit | Danamon
API Internal: API Gateway Analytics
1 | Matikan service API Gateway Analytics v7.7-May25 pada server Staging 10.194.120.208 dan 10.192.120.202 | 11/14/2025 | 18:50 | 19:20 | 30 menit | Naufal (SPS) | DB sudah masterslave
2 | Rsync folder Axway-7.7.0 dari Staging ke Production | 11/14/2025 | 22:30 | 23:20 | 50 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
rsync -av1HX /apps/Axway-7.7.0 apim@ipremotehost:/apps/Axway-7.7.0_may25
10.194.120.208 → 10.194.118.20
10.192.120.202 → 10.192.118.20
3 | Matikan service API Gateway Analytics v7.7-May23 pada server Production 10.194.118.20 dan 10.192.118.20 | 11/15/2025 | 2:00 | 2:02 | 2 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup | Downtime
4 | Rename instalasi folder API Gateway Analytics v7.7-May23 mennjadi /apps/Axway-7.7.0_aug23 | 11/15/2025 | 2:02 | 2:05 | 3 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
5 | Rename instalasi folder Axway-7.7.0_may25 menjadi Axway-7.7.0 | 11/15/2025 | 2:05 | 2:08 | 3 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
10.192.120.202 → 10.192.118.20
6 | Start Service API Gateway Analytics v7.7-May25 pada 10.194.118.20 dan 10.192.118.20 | 11/15/2025 | 2:08 | 2:11 | 3 menit | SPS (PIC2) | Service Online
PAT IT
*Details all activity that IT can ensure all process is running/deploy as expected
API EXTERNAL: API Gateway dan Cassandra
1 | Check API Gateway Manager v7.7-May25 | 11/15/2025 | 0:35 | 0:50 | 15 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
1.a | Login WEB UI API Gateway Manager
1.b | Check dashboard topology
1.c | Check traffic API
1.d | Pada WEB UI Akses KPS
1.e | Pada CLI akses managedomain
1.f | Pada CLI akses kpsadmin
1.g | Test Deploy instance bergantian (sekuensial) dengan CICD |  |  |  |  | Rizky (Danamon), Cepi (Danamon) & Lukman (SPS) & tim appsup
2 | Check API Manager v7.7-May25 | 11/15/2025 | 0:50 | 0:52 | 2 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
2.a | Login Web UI API Manager
2.b | Check API
3 | Akses Cassandra | 11/15/2025 | 0:52 | 0:55 | 3 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
3.a | Cluster check (nodetool status)
3.b | Login cassandra (cqlsh)
4 | Monitoring traffic | 11/15/2025 | 0:55 | 3:00 | 120 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
API External: External API Gateway Analytics
1 | Check login web UI API Gateway Manager | 11/15/2025 | 1:07 | 1:10 | 13 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
receive event from API Management External
Display the data
Generate pdf
API External: Sandbox API Management
1 | Check API Gateway Manager v7.7-May25 | 11/15/2025 | 1:30 | 1:45 | 15 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
1.a | Login WEB UI API Gateway Manager
1.b | Check dashboard topology
1.c | Check traffic API
1.d | Pada WEB UI Akses KPS
1.e | Pada CLI akses managedomain
1.f | Pada CLI akses kpsadmin
1.g | Test Deploy instance
2 | Check API Manager v7.7-May25 | 11/15/2025 | 1:45 | 1:47 | 2 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
2.a | Login Web UI API Manager
2.b | Check API
3 | Akses Cassandra | 11/15/2025 | 1:47 | 1:50 | 3 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
3.a | Cluster check (nodetool status)
3.b | Login cassandra (cqlsh)
4 | Monitoring traffic | 11/15/2025 | 1:50 | 3:00 | 70 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
API External Sandbox API Portal
1 | Login Joomla Administrator Interface | 11/15/2025 | 2:30 | 2:35 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
Pastikan tidak ada pop error
2 | Login api manager user | 11/15/2025 | 2:35 | 2:45 | 10 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
Pastikan semua laman bisa diakses
API INTERNAL: API Gateway dan Cassandra
1 | Check API Gateway Manager v7.7-May25 | 11/15/2025 | 1:40 | 1:55 | 15 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
1.a | Login WEB UI API Gateway Manager
1.b | Check dashboard topology
1.c | Check traffic API
1.d | Pada WEB UI Akses KPS
1.e | Pada CLI akses managedomain
1.f | Pada CLI akses kpsadmin
1.g | Deploy instance bergantian dengan CICD |  |  |  |  | Rizky & Cepi (Danamon) & Naufal (SPS) & tim appsup
2 | Check API Manager v7.7-May25 | 11/15/2025 | 1:55 | 1:57 | 2 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
2.a | Login Web UI API Manager
2.b | Check API
3 | Akses Cassandra | 11/15/2025 | 1:57 | 2:00 | 3 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
3.a | Cluster check (nodetool status)
3.b | Login cassandra (cqlsh)
4 | Monitoring traffic | 11/15/2025 | 2:00 | 3:00 | 60 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
API Internal: API Gateway Analytics
1 | Check login web UI API Gateway Analytics | 11/15/2025 | 2:11 | 2:21 | 10 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
receive event from API Management
Display the data
Generate pdf
Go / No Go Decision Implementation
1 | *Decision given by GHIT | 11/15/2025 |  |  |  | < GHIT Name>
(* Mandatory action, please do not eliminated)
PAT User (Refer to separate PAT Script)
Rollback Plan
API EXTERNAL: API Gateway dan Cassandra
1 | Stop Service API Gateway v7.7-May 25 dan Cassandra 4.1.8 | 11/15/2025 | 3:00 | 0:07 | 7 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Downtime
1.a | Disable port traffic melalui API Gateway Manager dashboard
1.b | Shutdown service nodemanager dan instance
1.c | Shutdown service Cassandra
/apps/Axway-7.7.0/cassandra/bin/nodetool drain
ps -ef¦grep cassandra
kill -9 <pid>
2 | Rename folder Axway-7.7.0 menjadi Axway-7.7.0_may25 | 11/15/2025 | 3:07 | 3:09 | 2 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
3 | Rename folder Axway-7.7.0_aug23 menjadi Axway-7.7.0 | 11/15/2025 | 3:09 | 3:10 | 1 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
4 | Start service Cassandra v4.0.10 | 11/15/2025 | 3:10 | 3:15 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
5 | Start service API Gateway v7.7_aug23: Node Manager dan Instance | 11/15/2025 | 3:15 | 3:25 | 10 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Service On
6 | Check API Gateway v7.7-May25 | 11/15/2025 | 3:25 | 3:40 | 15 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
6.a | Login API Gateway Manager dan check traffic
6.b | Login API Manager
6.c | Login Cassandra
API External: API Gateway Analytics
1 | Stop Service API Gateway Analytics v7.7-May 25 | 11/15/2025 | 3:40 | 3:43 | 3 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Downtime
2 | Rename folder Axway-7.7.0 menjadi Axway-7.7.0_may25 | 11/15/2025 | 3:43 | 3:48 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
3 | Rename folder Axway-7.7.0_aug23 menjadi Axway-7.7.0 | 11/15/2025 | 3:48 | 3:52 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
4 | Start service API Gateway Analytics v7.7_aug23 | 11/15/2025 | 3:52 | 3:57 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
5 | Login Web Admin Analytics and check dashboard | 11/15/2025 | 3:57 | 4:07 | 10 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Service ON
API External: Sandbox API Management
1 | Stop Service API Gateway v7.7-May 25 (cassandra dan node manager) | 11/15/2025 | 4:07 | 4:12 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Downtime
2 | Rename folder Axway-7.7.0 menjadi Axway-7.7.0_may25 | 11/15/2025 | 4:12 | 4:17 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
3 | Rename folder Axway-7.7.0_aug23 menjadi Axway-7.7.0 | 11/15/2025 | 4:17 | 4:22 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
4 | Start service API Gateway v7.7_aug23 | 11/15/2025 | 4:22 | 4:27 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
5 | Check API Gateway v7.7-May25 | 11/15/2025 | 4:27 | 4:37 | 10 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Service ON
5.a | Login API Gateway Manager dan check traffic
5.b | Login API Manager
5.c | Login Cassandra
API External: Sandbox API Portal
1 | Matikan service mysql dan httpd API Portal v7.7-May25 | 11/15/2025 | 4:37 | 4:42 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Downtime
2 | Rename folder mysql dan htdoc API Portal v7.7-May25 di prod | 11/15/2025 | 4:42 | 4:47 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
3 | Rename folder mysql dan htdoc API Portal v7.7-Aug23 di to existing folder name | 11/15/2025 | 4:47 | 4:52 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup
4 | Start service mysql dan httpd API Portal v7.7_aug23 | 11/15/2025 | 4:52 | 4:57 | 5 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Service ON
5 | Login API Portal (joomla dan API Portal) | 11/15/2025 | 4:57 | 5:07 | 10 menit | Cepi (Danamon) & Lukman (SPS) & tim appsup | Service ON
API INTERNAL: API Gateway dan Cassandra
1 | Stop Service API Gateway v7.7-May 25 dan Cassandra 4.1.8 | 11/15/2025 | 3:00 | 3:07 | 7 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup | Downtime
1.a | Disable port traffic melalui API Gateway Manager dashboard
1.b | Shutdown service nodemanager dan instance
1.c | Shutdown service Cassandra
/apps/Axway-7.7.0/cassandra/bin/nodetool drain
ps -ef¦grep cassandra
kill -9 <pid>
2 | Rename folder Axway-7.7.0 menjadi Axway-7.7.0_may25 | 11/15/2025 | 3:07 | 3:09 | 2 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
3 | Rename folder Axway-7.7.0_aug23 menjadi Axway-7.7.0 | 11/15/2025 | 3:09 | 3:10 | 1 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
4 | Start service Cassandra v4.0.10 | 11/15/2025 | 3:10 | 3:15 | 5 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
5 | Start service API Gateway v7.7_aug23: Node Manager dan Instance | 11/15/2025 | 3:15 | 3:25 | 10 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup | Service On
6 | Check API Gateway v7.7-May25 | 11/15/2025 | 3:25 | 3:40 | 15 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
6.a | Login API Gateway Manager dan check traffic
6.b | Login API Manager
6.c | Login Cassandra
API INTERNAL: API Gateway Analytics
1 | Stop Service API Gateway Analytics v7.7-May 25 | 11/15/2025 | 3:40 | 3:43 | 3 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup | Downtime
2 | Rename folder Axway-7.7.0 menjadi Axway-7.7.0_may25 | 11/15/2025 | 3:43 | 3:48 | 5 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
3 | Rename folder Axway-7.7.0_aug23 menjadi Axway-7.7.0 | 11/15/2025 | 3:48 | 3:52 | 5 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
4 | Start service API Gateway Analytics v7.7_aug23 | 11/15/2025 | 3:52 | 3:57 | 5 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup
5 | Login Web Admin Analytics and check dashboard | 11/15/2025 | 3:57 | 4:07 | 10 menit | Cepi (Danamon) & Naufal (SPS) & tim appsup | Service ON